TECHNICAL & COMMERCIAL PROPOSAL

Project Title

(Project Nature description)

Prepared for: Customer name

Prepared by: Qmax Systems India Pvt. Ltd. / Qmax Systems LLC

Document: QMX-PRO-2026-SLMK-001  |  Rev 3.0  |  June 10, 2026

CONFIDENTIAL — Subject to NDA between Qmax & Customer Name

Table of Contents

Abbreviations & Acronyms	3

1. Executive Summary	6

2. Project Understanding & Requirements Compliance	8

2.1 Requirements Compliance Matrix	8

3. Technical Approach & System Architecture	10

3.1 System Block Diagram	10

3.2 Bandwidth Engineering	10

3.3 Key Component Strategy (FPGA selected; remaining devices finalized at architecture phase)	11

3.4 Mechanical & PCB Constraints (per O&M drawing PT-DT21-0227 Rev 1)	11

4. Complete Activity List (All Workstreams)	12

4.1 Program & Engineering Management	12

4.2 Hardware Workstream	12

4.3 FPGA / Firmware Workstream	12

4.4 Validation & Quality Workstream	13

5. Detailed FPGA Development Statement of Work	13

5.1 Work Package FP-A: Architecture & Specification	13

5.2 Work Package FP-B: MIPI CSI-2 Receiver	13

5.3 Work Package FP-C: Video Pipeline & Buffering	14

5.4 Work Package FP-D: 2.5 G Ethernet MAC & PCS	14

5.5 Work Package FP-E: UDP/IP Hardware Offload	14

5.6 Work Package FP-F: GVCP Control Engine	15

5.7 Work Package FP-G: GVSP Streaming Engine	15

5.8 Work Package FP-H: GenICam Compliance	15

5.9 Work Package FP-I: Control-Plane Soft-Core & Firmware	15

5.10 Work Package FP-J: Verification, Closure, Integration, Validation	16

5.11 FPGA Deliverables	16

6. Detailed Effort Estimation	17

6.1 Hardware Development — $35/hour	17

6.2 FPGA Development — $45/hour	18

6.3 Option A: ONVIF Output (Separate Line Item) — $45/hour	21

6.4 Program Cost Summary	21

7. Tools, Equipment & Software	22

7.1 Design & Development Tools	22

7.2 Test & Validation Equipment (Lab)	23

8. Validation Plan	24

Phase V1 — Hardware Verification (per board)	24

Phase V2 — MIPI Input Validation	24

Phase V3 — Ethernet & Protocol Validation	25

Phase V4 — Performance & Robustness	25

Phase V5 — Production Screening (all 20 prototypes)	26

9. Schedule (≈24 weeks, two PCB spins)	27

Gant Chart	28

10. Deliverables Summary	28

11. Assumptions, Scope Definition & Dependencies	29

11.1 Technical Assumptions	29

11.2 Customer Dependency Assumptions	30

12. In-Scope and Out-of-Scope Activities	31

12.1 In Scope	31

12.2 Out of Scope	32

Networking — Not Included	32

Security — Not Included	33

Camera / Image Processing Features — Not Included (Transparent-Bridge Principle)	33

13. Risk Register	34

14. Terms & Conditions	36

14.1 Commercial	36

14.2 Scope & Change Management	36

14.3 Intellectual Property	37

14.4 Confidentiality & Export Control	37

14.5 Warranty & Liability	37

14.6 Delivery & Acceptance	38

14.7 General	38

# Abbreviations & Acronyms

The following abbreviations and acronyms are used throughout this document.

| Abbreviation | Expansion |
| --- | --- |
| AES | Advanced Engineering Services |
| AIA | Automated Imaging Association |
| ARP | Address Resolution Protocol |
| BoM | Bill of Materials |
| BRAM | Block RAM |
| CAT | Category (cable specification, e.g. CAT 6a) |
| CDR | Critical Design Review |
| CSI-2 | Camera Serial Interface 2 (MIPI standard) |
| DFM | Design for Manufacturability |
| DHCP | Dynamic Host Configuration Protocol |
| D-PHY | Differential Physical Layer (MIPI) |
| ECC | Error Correction Code |
| ECO | Engineering Change Order |
| EMC | Electromagnetic Compatibility |
| EMI | Electromagnetic Interference |
| ESD | Electrostatic Discharge |
| FCS | Frame Check Sequence |
| FPGA | Field-Programmable Gate Array |
| FPS | Frames Per Second |
| GenICam | Generic Interface for Cameras |
| GigE | Gigabit Ethernet |
| GVCP | GigE Vision Control Protocol |
| GVSP | GigE Vision Streaming Protocol |
| HDL | Hardware Description Language |
| HSIO | High-Speed I/O (FPGA SerDes interface) |
| ICD | Interface Control Document |
| ICMP | Internet Control Message Protocol |
| IEEE | Institute of Electrical and Electronics Engineers |
| IP | Internet Protocol / Intellectual Property (context-dependent) |
| ITAR | International Traffic in Arms Regulations |
| JTAG | Joint Test Action Group |
| LLA | Link-Local Address |
| LRAM | Large RAM (Lattice on-chip memory) |
| MAC | Media Access Control |
| MIPI | Mobile Industry Processor Interface |
| MTU | Maximum Transmission Unit |
| NDA | Non-Disclosure Agreement |
| O&M | Outline and Mounting (drawing) |
| ONVIF | Open Network Video Interface Forum |
| PCB | Printed Circuit Board |
| PCS | Physical Coding Sublayer |
| PDR | Preliminary Design Review |
| PHY | Physical Layer transceiver |
| PD | Powered Device (PoE) |
| PoE | Power over Ethernet |
| PSE | Power Sourcing Equipment (PoE) |
| QSPI | Quad Serial Peripheral Interface |
| RTL | Register Transfer Level |
| RTSP | Real-Time Streaming Protocol |
| RTP | Real-Time Transport Protocol |
| SFNC | Standard Features Naming Convention (GenICam) |
| SGMII | Serial Gigabit Media Independent Interface |
| SI/PI | Signal Integrity / Power Integrity |
| SoC | System on Chip |
| TLS | Transport Layer Security |
| TRR | Test Readiness Review |
| TSN | Time-Sensitive Networking |
| UDP | User Datagram Protocol |
| UVM | Universal Verification Methodology |
| VHDL | VHSIC Hardware Description Language |
| VLAN | Virtual Local Area Network |
| XML | Extensible Markup Language |

# 1. Executive Summary

Qmax Systems is pleased to submit this proposal to Advanced Engineering Services (AES) for the turnkey development of an FPGA-based MIPI CSI-2 (4-lane) to Ethernet GigE Vision v2.x adapter board for Sellmark Corporation's thermal imaging product line. The scope covers hardware design, PCB layout, custom FPGA development (with no licensed HDL, IP cores, or firmware), manufacturing package, 20 functional prototypes, and full testing & validation with documentation.

Key technical decision — bandwidth: Full 1280 × 1024 transmission at 60 FPS requires ≈1.26 Gbps (RAW16) and ≈1.89 Gbps (RGB888) of payload bandwidth, which exceeds 1000BASE-T capacity. Qmax therefore proposes a 2.5GBASE-T physical layer — fully supported by the specified CAT6a jack — running the GigE Vision v2.x protocol stack. This carries both pixel formats uncompressed at full frame rate with comfortable margin, with no compression and no change to the GigE Vision/GenICam software ecosystem on the host side.

| Commercial Summary | Hours | Price (USD) |
| --- | --- | --- |
| Hardware development (design, layout, mfg package, bring-up) @ $35/hr | 10 | $100 |
| FPGA development (GigE Vision v2.x, GenICam, validation) @ $45/hr | 10 | $100 |
| Prototype materials & assembly — two PCB spins: Spin 1 Qty 5 + Spin 2 Qty 20 (budgetary, at-cost pass-through) | — | $200 (est.) |
| Base program total | 20 | $400 |
| Option: ONVIF output (flash + source) — separate line item per Req. 3 & 9.3 | 5 | $100 |

Architecture decision — single-chip, DRAM-less: the design is baselined on the Lattice CertusPro-NX-50 FPGA — an established, long-lifecycle US device with hardened SerDes/PCS for the 2.5 G link. Because the 2.5 G egress bandwidth exceeds the 1.9 Gbps worst-case ingress, the video path is true stream-through using on-chip RAM only: no external DRAM device, routing or power rails. This minimizes component cost and is decisive for fitting the 38 × 38 mm board envelope. GVSP packet resend is provided via an on-chip window sized for point-to-point links (Assumption A-17).

Two PCB spins included: the program includes a Spin 1 engineering build (Qty 5) for bring-up and debug, a full ECO cycle incorporating all findings, and a Spin 2 deliverable build (Qty 20) — the standard de-risked path for a first-pass high-density 2.5 G design.

Indicative schedule: approximately 24 weeks from kickoff to delivery of 20 validated Spin 2 prototypes and the complete documentation package (Section 9).

# 2. Project Understanding & Requirements Compliance

The adapter board receives video from Sellmark's ITAR-controlled thermal camera core over a 4-lane MIPI CSI-2 interface and streams it over Ethernet as a fully compliant GigE Vision v2.x / GenICam device. Validation will use an off-the-shelf 4-lane MIPI camera selected by Qmax; the source code will be structured so Sellmark can independently adapt the MIPI pin-out, timing and ICD/API to their thermal core without Qmax requiring access to ITAR data.

## 2.1 Requirements Compliance Matrix

| Req. | Requirement (summary) | Compliance | Approach / Remarks |
| --- | --- | --- | --- |
| 1 | Design, layout, prototyping, programming, prototype validation | Comply | Full scope included |
| 2 | Input: 4-lane MIPI CSI | Comply | Custom CSI-2 RX, soft D-PHY 4-lane (2.5× lane-rate margin) |
| 3 | Output: GigE Vision v2.x, GenICam compliant; ONVIF as separate line item | Comply | Custom GVCP/GVSP stack; ONVIF priced as Option A |
| 4 | Power over Ethernet | Comply | IEEE 802.3at Class 4 PD front-end |
| 5 | 4.5 V / 3.7 W sensor power over MIPI connector | Comply | Dedicated regulated rail, current-limited & monitored |
| 6 | CAT 6a compatible Ethernet jack | Comply | Shielded RJ45; CAT6a supports 2.5GBASE-T to 100 m |
| 7 | No licensed HDL, IP cores, or firmware | Comply | All RTL & firmware written by Qmax; only vendor-provided device primitives (SerDes/MPCS, PLL, I/O macros) used — see Assumption A-3 |
| 8 | Full 1280 × 1024, RAW16 and RGB888 @ 60 FPS over Ethernet | Comply | 2.5GBASE-T PHY; uncompressed stream-through; see Section 3.2 |
| 9.1 | Altium (preferred) or KiCad deliverables | Comply | Our preference is Cadence Allegro |
| 9.2 | 20 functional physical prototypes | Comply | Fab + assembly + 100% functional test |
| 9.3 | FPGA flash & source for GigE Vision; ONVIF separate | Comply | Full RTL, firmware, build scripts, bitstream |
| 9.4 | Testing & validation documentation | Comply | Plan, procedures, reports (Section 8) |
| 10 | Validation with off-the-shelf 4-lane MIPI camera | Comply | Reference camera selected at architecture phase |
| 11 | Source formatted/documented for customer MIPI/ICD adaptation | Comply | Parameterized RTL + porting guide |
| 12 | Customer provides PCBA O&M (dimensions, keep-outs, connectors) | Noted | Drawing PT-DT21-0227 Rev 1 received; 38 × 38 mm, 1.5 mm height keep-out zone, Samtec SS4-20-3.00-L-D-TR |
| 13 | Customer provides mfg file templates & formatting guidance | Noted | Will be requested at kickoff |

# 3. Technical Approach & System Architecture

## 3.1 System Block Diagram

## 3.3 Key Component Strategy

| Function | Candidate devices | Selection drivers |
| --- | --- | --- |
| FPGA (selected) | Lattice CertusPro-NX-50 (LFCPNX-50) | Hardened SerDes/MPCS (8b/10b) for 2.5 G SGMII/2500BASE-X; ~2.9 Mb EBR/LRAM for stream-through buffering + resend window; soft D-PHY on HSIO with 2.5× lane-rate margin; established US vendor with AEC-Q100-class family and strong lifecycle policy |
| Frame memory | None — DRAM-less architecture | Stream-through with on-chip BRAM elastic buffers; limited GVSP resend window in EBR/LRAM (Assumption A-17); removes memory device, routing and rails from the 38 × 38 mm board |

## 3.4 Mechanical & PCB Constraints (per O&M drawing PT-DT21-0227 Rev 1)

- Board outline 38 × 38 mm with 4× R2.50 corner radii; 4× mounting holes with R1.00 features per drawing

- Samtec SS4-20-3.00-L-D-TR MIPI connector at the position defined by datums A/B/C

# 4. Complete Activity List

## 4.1 Program & Engineering Management

- Project kickoff, communication plan, weekly status reporting to AES

- Requirements clarification log and ICD management with AES / Sellmark

- Risk register maintenance and milestone gate reviews (PDR, CDR, TRR)

## 4.2 Hardware Workstream

- System architecture, power budget, component selection & BoM

- Power tree design: PoE PD, isolation, POL rails, 4.5 V sensor supply

- Schematic capture in Altium Designer with design-rule reviews

- Stack-up & impedance planning; placement study within 38 × 38 mm envelope

- PCB layout, length matching (MIPI/SerDes), high-speed routing, DFM

- Post-layout SI/PI verification and report

- Manufacturing package generation to customer templates

- Prototype fabrication & assembly management — Qty 20

- Board bring-up: power, clocks, JTAG, SerDes eye scan, PHY link, PoE negotiation

- Hardware test reports and documentation

## 4.3 FPGA / Firmware Workstream

- FPGA architecture specification, register map, verification plan

- MIPI CSI-2 4-lane receiver development (D-PHY + protocol layer)

- Video pipeline: RAW16 / RGB888 handling, test pattern, statistics

- On-chip BRAM elastic buffering and resend-window management (DRAM-less)

- Custom 2.5 G Ethernet MAC + PCS (SGMII/2500BASE-X) development

- Hardware UDP/IP stack: ARP, ICMP, DHCP/LLA, IP configuration

- GVCP engine: discovery, bootstrap registers, access control, heartbeat

- GVSP engine: packetization, block IDs, resend buffer, rate scheduling

- GenICam XML and SFNC-aligned feature implementation

- Soft-core control processor and bare-metal firmware

- Simulation testbenches and regression suite

- Synthesis, place & route, timing closure, resource/power reports

- Lab integration: first light over MIPI, end-to-end video over Ethernet

- GigE Vision compliance & interoperability validation

- Source documentation and customer porting guide

## 4.4 Validation & Quality Workstream

- Validation plan & test procedure authoring (reviewed at TRR)

- Functional, performance, robustness and soak testing (Section 8)

- 100% functional screening of all 20 prototypes with test records

- Final validation report and delivery review

# 5. Detailed Development Statement of Work

All RTL (VHDL/SystemVerilog), firmware (C), constraints, build scripts and testbenches are developed by Qmax from scratch in compliance with Requirement 7 (no licensed HDL, IP cores, or firmware). Vendor silicon hard primitives (SerDes/MPCS, PLL, I/O and delay macros) are device features, not licensed IP cores; this interpretation is recorded as Assumption A-3 for AES/Sellmark concurrence.

## 5.1 Work Package FP-A: Architecture & Specification

- Dataflow and clock-domain architecture; latency and buffer-depth analysis at 60 FPS

- FPGA device selection with utilization budget (logic, BRAM, SerDes, I/O) and ≥25% growth margin

- Register map specification (bootstrap + manufacturer-specific space)

- Verification plan: coverage goals, protocol checkers, regression definition

- Exit criteria: architecture specification approved at PDR

## 5.2 Work Package FP-B: MIPI CSI-2 Receiver

- D-PHY receive front-end: HS-RX per lane, LP-RX, lane initialization, clock-lane handling, per-lane deskew and word alignment

- CSI-2 low-level protocol: packet header decode, ECC correction, payload CRC checking, short/long packet handling, virtual channels

- Pixel decode for RAW16 and RGB888 data types; frame/line synchronization

- Parameterized pin-out and timing (Req. 11) so Sellmark can retarget to the ITAR thermal core

- Exit criteria: error-free frame capture from reference camera at full rate, ECC/CRC error injection tests pass in simulation

## 5.3 Work Package FP-C: Video Pipeline & Buffering

- Line assembly and pixel unpacking into AXI-Stream video

- On-chip EBR/LRAM elastic buffering: backpressure-safe stream-through design (2.5 G egress > 1.9 Gbps ingress); no external memory

- Internal test-pattern generator (ramp, color bars, moving counter) for sensor-independent validation and production test

- Exit criteria: zero frame drops at 60 FPS in 24-hour loopback test with worst-case resend load active

## 5.4 Work Package FP-D: 2.5 G Ethernet MAC & PCS

- Custom MAC: framing, FCS generation/checking, jumbo frames to 9 KB, pause-frame handling, statistics counters

- PCS for 2500BASE-X / SGMII over FPGA SerDes; auto-negotiation with external 2.5GBASE-T PHY; MDIO controller

- Exit criteria: line-rate iperf-class UDP saturation testing ≥2.3 Gbps sustained

## 5.5 Work Package FP-E: UDP/IP Hardware Offload

- Streaming-path IPv4/UDP header generation at line rate; checksum offload

- ARP responder/requester, ICMP echo, IGMP (for multicast streaming option)

- IP configuration state machine per GigE Vision: persistent IP, DHCP, Link-Local Address fallback

- Exit criteria: device reachable & discoverable in all three IP modes

## 5.6 Work Package FP-F: GVCP Control Engine

- GigE Vision v2.x bootstrap register space and device discovery (DISCOVERY_CMD/ACK broadcast handling)

- READREG / WRITEREG / READMEM / WRITEMEM command processing with proper ACK/NACK and pending-ACK semantics

- Control channel privilege management: exclusive / control / monitor access, heartbeat timeout & recovery

- Exit criteria: passes GVCP sections of the GigE Vision Validation Framework

# 6. Detailed Effort Estimation

## 6.1 Hardware Development — $ /hour

| ID | Activity & description | Hours | Cost |
| --- | --- | --- | --- |
| HW-01 | Requirements analysis, system architecture & ICD review — Detailed review of requirements, O&M drawing, MIPI sensor interface definition, power budget, architecture document | 48 |  |
| HW-02 | Component selection & engineering BoM — Lattice CertusPro-NX-50 FPGA, 2.5GBASE-T PHY, PoE PD controller, DC-DC converters, QSPI flash, MIPI connector (Samtec SS4-20), magnetics, RJ45; availability & lifecycle check — DRAM-less architecture, no external memory | 48 |  |
| HW-03 | Power architecture design — PoE PD front-end (IEEE 802.3at, Class 4), isolated flyback, point-of-load rails (FPGA core/IO/transceiver, PHY), 4.5 V / 3.7 W sensor supply over MIPI connector, sequencing & monitoring | 40 |  |
| HW-04 | Schematic capture (Altium Designer) — Full schematic: CertusPro-NX-50 banks & configuration, 2.5G PHY + magnetics + RJ45 (CAT6a), PoE PD section, MIPI CSI-2 connector & power, clocking, QSPI, JTAG/debug, status LEDs, ESD/EMC protection — simplified by DRAM-less architecture | 144 |  |
| HW-05 | Pre-layout engineering — Layer stack-up definition (6 layer target, enabled by DRAM-less BoM), impedance plan (MIPI 100 Ω diff, Ethernet MDI, SerDes pairs), constraint set, placement study against 38 × 38 mm outline, 1.5 mm height keep-out & mounting per O&M drawing PT-DT21-0227 | 32 |  |
| HW-06 | PCB layout (Altium Designer) — High-density layout within customer O&M envelope: MIPI lane routing, SerDes pair routing to PHY, 2.5G MDI routing, PoE isolation spacing, thermal copper for FPGA; DRC clean to customer fab templates — no DRAM bus to route | 176 |  |
|  | Subtotal | 968 | $33,880 |

## 6.4 Program Cost Summary

| Line item | Hours | Rate | Cost (USD) |
| --- | --- | --- | --- |
| Hardware development | 968 |  |  |
| FPGA development (GigE Vision v2.x) | 2136 |  |  |
| Prototype materials, fab & assembly — two spins (Qty 5 + Qty 20), budgetary, billed at cost with documentation | — |  |  |
| Base program total | 3104 |  |  |
| Option A — ONVIF output (flash + source) | 560 |  |  |
| Total with Option A | 3664 |  |  |

# 7. Tools, Equipment & Software

## 7.1 Design & Development Tools

| Tool | Purpose |
| --- | --- |
| Altium Designer | Schematic capture, PCB layout, manufacturing outputs (Req. 9.1 preferred format) |
| Lattice Radiant | Synthesis, place & route, timing closure, on-chip debug (Reveal) for CertusPro-NX-50 |
| Questa/ModelSim + Verilator/cocotb | RTL simulation, testbenches, nightly regression |
| SI/PI analysis tooling (HyperLynx-class) | Pre/post-layout signal & power integrity verification |
| GCC cross-toolchain (MicroBlaze/RISC-V) | Soft-core firmware build |
| Git + CI runner | Version control, reproducible builds, regression automation |
| Wireshark with GVCP/GVSP dissectors | Protocol debugging and capture analysis |
| Aravis (open source) and eBUS SDK runtime | Independent GenTL host stacks for interoperability |
| AIA GigE Vision Validation Framework | Standard conformance testing (membership/access via A3) |
| ONVIF Device Test Tool (Option A only) | ONVIF conformance runs |

## 7.2 Test & Validation Equipment (Lab)

| Equipment | Use in this program |
| --- | --- |
| 4-channel oscilloscope, ≥2.5 GHz BW with D-PHY/Ethernet decode | MIPI lane signal quality, PHY MDI checks, power-rail transients |
| MIPI CSI-2 protocol analyzer / D-PHY probe set | Lane traffic capture, ECC/CRC error verification against reference camera |
| Reference 4-lane MIPI CSI-2 camera module (OTS, Qmax-selected, e.g., IMX-series 4-lane module) | Validation vehicle per Req. 10 |
| 2.5/5/10 GbE managed switch with 802.3at/bt PoE | Link, PoE class negotiation, network topology tests |
| PoE PD/PSE tester & 802.3at injector | PoE power budget, inrush, fault and classification tests |
| Host PC with 2.5 GbE and 10 GbE NICs | Streaming host, throughput and interoperability testing |
| Ethernet traffic generator / iperf-class load setup | Line-rate saturation, congestion and resend stress |
| JTAG programmers/debuggers (FPGA + soft-core) | Bring-up, flash programming, on-chip debug |
| Bench PSUs, electronic load, precision DMMs | Power tree verification, 4.5 V / 3.7 W sensor rail load test |
| Thermal camera + thermocouple logger | Thermal characterization at sustained 60 FPS load |
| Cable set: CAT6a (1 m–100 m), field-terminated samples | Link margin across cable lengths |
| ESD-safe assembly/rework station, microscope | Prototype screening, rework, first-article inspection |

# 8. Validation Plan

Validation is executed in five phases. Each phase has documented procedures, pass/fail criteria and recorded results; the consolidated Validation Report is a contract deliverable (Req. 9.4). Validation uses the Qmax-selected off-the-shelf 4-lane MIPI camera (Req. 10) plus the internal test-pattern generator for sensor-independent coverage.

## Phase V1 — Hardware Verification (per board)

| Test | Method | Pass criteria |
| --- | --- | --- |
| Power-on & rail check | Sequenced power-up, all rails measured under load | All rails within ±3% of nominal |
| PoE negotiation | 802.3at PSE/injector, class & power measurement | Class 4 negotiation; stable operation at full load |
| Sensor power rail | Electronic load on MIPI connector power pins | 4.5 V ±5% at 3.7 W; current limit & recovery verified |
| Clocks & configuration | Oscilloscope + JTAG; bitstream load from QSPI | All clocks in spec; auto-configuration < 2 s |
| On-chip buffer stress | Worst-case ingress burst + forced resend traffic via test-pattern generator | Zero overflow/underflow flags in 1-hour stress |
| Thermal | Sustained 60 FPS streaming at 25 °C ambient | All component temperatures within derated limits |

## Phase V2 — MIPI Input Validation

| Test | Method | Pass criteria |
| --- | --- | --- |
| D-PHY signal integrity | Scope/protocol probe on all 4 lanes at full rate | Eye/levels within D-PHY spec; no LP/HS violations |
| CSI-2 protocol | Analyzer capture; ECC/CRC counters | Zero uncorrected errors over 1-hour capture |
| Format decode | RAW16 and RGB888 streams from reference camera | Pixel-exact frames vs. analyzer reference |
| Error robustness | Injected ECC/CRC errors (simulation + cable margin tests) | Errors detected, flagged, no pipeline lock-up |

## Phase V3 — Ethernet & Protocol Validation

| Test | Method | Pass criteria |
| --- | --- | --- |
| Link & MDI | Link-up across 1 m–100 m CAT6a at 2.5 G | Stable link, zero FCS errors over 10^12 bits |
| IP configuration | Persistent IP, DHCP, LLA modes | Discoverable & reachable in all modes |
| GVCP conformance | GigE Vision Validation Framework | All applicable mandatory tests pass |
| GVSP streaming | Validation Framework + Wireshark analysis | Compliant leader/payload/trailer, block IDs, timestamps |
| GenICam | XML schema validation; feature exercise from 2 host stacks | Enumeration and control in Aravis and eBUS SDK |

## Phase V4 — Performance & Robustness

| Test | Method | Pass criteria |
| --- | --- | --- |
| Sustained throughput | RAW16 and RGB888 @ 60 FPS, 24-hour soak | Zero dropped/corrupted frames at host |
| Resend recovery | Forced packet loss (switch impairment / host filter) up to 1% | All frames recovered via GVSP resend; no corruption |
| Concurrent control + stream | Register access during streaming | No frame disturbance; correct GVCP responses |
| Power cycling | 1,000 automated power cycles while streaming | 100% recovery to streaming state; settings retained |
| Long-cable margin | 100 m CAT6a at full rate | Sustained 60 FPS, link stable |

## Phase V5 — Production Screening (all 20 prototypes)

- Automated functional test sequence: power, PoE, configuration, test-pattern streaming at 60 FPS, MIPI loop check with reference camera on sample basis

- Serialization, test record per unit, label and pack

- Acceptance: 20/20 units pass full functional screen; report issued with per-unit data

# 9. Schedule (≈24 weeks, two PCB spins)

| Milestone | Week | Contents |
| --- | --- | --- |
| Kickoff | W1 | Requirements baseline, template handover (Req. 13), ICD review |
| PDR | W3 | Architecture spec, component selection, FPGA device freeze, reference camera selection |
| Schematic release | W5 | Schematic review complete, long-lead parts ordered (both spins where practical) |
| CDR / Spin 1 release | W8 | Layout + SI/PI report approved; Spin 1 manufacturing package to fab |
| Spin 1 boards in lab | W12 | 5 engineering units assembled; bring-up & debug start. FPGA development proceeds in parallel from W1 with simulation-first methodology |
| First video over Ethernet | W16 | End-to-end MIPI → GigE Vision streaming demonstrated on Spin 1 |
| Spin 2 (ECO) release | W18 | All Spin 1 findings incorporated; updated manufacturing package to fab |
| Spin 2 boards in lab | W21 | 20 deliverable units assembled; regression verification |
| TRR & validation complete | W23 | Phases V1–V4 complete on Spin 2 hardware |
| Final delivery | W24 | 20 screened Spin 2 prototypes, all sources, manufacturing package, validation report, porting guide |

ONVIF Option A, if ordered, adds approximately 10–12 weeks and can run partially in parallel after W21.

## Gant Chart

# 10. Deliverables Summary

- Altium Designer source: schematic, PCB, libraries; complete manufacturing package per customer templates (Req. 9.1, 13)

- 20 functional, individually screened prototypes with per-unit test records (Req. 9.2)

- FPGA flash images and complete source: RTL, firmware, constraints, build scripts, testbenches for GigE Vision v2.x (Req. 9.3)

- GenICam XML source and register map documentation

- Porting guide for MIPI pin-out, timing and ICD/API adaptation (Req. 11)

- Validation plan, procedures and consolidated validation report (Req. 9.4)

- Option A (if ordered): ONVIF flash image, source code and conformance report

# 11. Assumptions, Scope Definition & Dependencies

## 11.1 Technical Assumptions

- A-1 — Physical layer: 2.5GBASE-T is acceptable to meet Requirement 8 (full 1280 × 1024 RAW16/RGB888 @ 60 FPS) over the specified CAT6a jack. Host PC requires a ≥2.5 GbE NIC.

- A-2 — PoE budget: the PoE source (switch/injector) is IEEE 802.3at (Class 4, 25.5 W) capable, covering board load plus the 4.5 V / 3.7 W sensor supply.

- A-3 — “No licensed HDL/IP-cores/firmware” (Req. 7) excludes FPGA silicon hard primitives (SerDes/MPCS, PLL, I/O and delay macros) and vendor device-support files required to target the silicon. All synthesizable RTL and all firmware are Qmax-authored originals delivered with full source. AES/Sellmark written concurrence requested at kickoff.

- A-4 — Operating modes: RAW16 and RGB888 are alternative streaming modes selected via GenICam PixelFormat, not simultaneous dual streams.

- A-5 — Single sensor input: one 4-lane MIPI CSI-2 input and one Ethernet output; no multi-camera aggregation.

- A-6 — Reference camera: validation uses a Qmax-selected off-the-shelf 4-lane MIPI camera (Req. 10). Where the camera’s native formats do not cover RAW16, the internal test-pattern generator provides pixel-exact path coverage.

- A-7 — ITAR isolation: no ITAR-controlled data, documentation or hardware is transferred to Qmax. Adaptation to the thermal core is performed by Sellmark using the delivered porting guide (Req. 11).

- A-8 — GigE Vision licensing: Qmax will hold/obtain A3 GigE Vision registration as required for a compliant device. Formal plugfest certification, if desired, is quoted separately.

- A-9 — Two PCB spins are included in this proposal: Spin 1 engineering build (Qty 5) for bring-up/debug, and Spin 2 deliverable build (Qty 20) after a full ECO cycle. A third spin, if ever required, would be handled via change order.

- A-10 — Mechanical envelope: O&M drawing PT-DT21-0227 Rev 1 is final for outline, mounting, keep-outs and connector positions, except RJ45 vertical position (negotiable per drawing Note 1). The 1.5 mm component-height restriction applies only within the defined keep-out zone, not board-wide.

- A-11 — ONVIF scope (Option A): targets Profile S with RTSP streaming; codec and achievable frame rate agreed during scoping (uncompressed 60 FPS is outside typical ONVIF VMS usage).

## 11.2 Customer Dependency Assumptions

- A-12 — AES/Sellmark provide manufacturing file templates and formatting guidance (Req. 13) within 2 weeks of kickoff.

- A-13 — Review feedback at design gates (PDR, CDR, TRR) returned within 5 business days; delays shift the schedule day-for-day.

- A-14 — AES designates a single consolidated technical point of contact for requirement clarifications.

- A-15 — Component availability is as of proposal date; allocation/EOL events on long-lead parts (FPGA, PHY) may require schedule/cost adjustment via change order.

- A-16 — Prototype materials, fabrication and assembly are billed at cost (pass-through with documentation); the $18,000 figure for both spins is budgetary.

- A-17 — DRAM-less architecture: GVSP packet resend is supported via a limited on-chip window (~360 KB, covering the most recent packets), sized for transient loss on point-to-point or lightly switched links. GVSP resend is an optional GigE Vision feature; full-frame resend would require external memory and is available as a change order. Sellmark concurrence requested at kickoff.

# 12. In-Scope and Out-of-Scope Activities

## 12.1 In Scope

- System architecture and FPGA / PHY / PoE component selection

- Hardware schematic design in Altium Designer

- PCB layout (impedance-controlled, within customer O&M envelope) with SI/PI verification

- Complete manufacturing package (Gerber/ODB++, drill, IPC netlist, fab/assembly drawings, pick-and-place, BoM, 3D STEP) per customer templates — released for both spins

- Two PCB spins: Spin 1 engineering build (Qty 5), full ECO cycle, Spin 2 deliverable build (Qty 20)

- FPGA RTL development, fully original: MIPI CSI-2 4-lane RX (soft D-PHY), video pipeline, on-chip buffering (DRAM-less), 2.5 G MAC over hardened MPCS, hardware UDP/IP, GVCP, GVSP, GenICam XML

- Soft-core control processor and bare-metal firmware (DHCP/LLA, persistence, field update)

- Simulation testbenches, regression suite, timing closure

- First-article inspection and 100% functional screening of the 20 deliverable units

- Board bring-up and full 5-phase validation (hardware, MIPI, protocol conformance, performance/soak, production screening)

- GigE Vision Validation Framework testing and interoperability verification on two independent GenTL host stacks

- Complete documentation: design description, register map, validation plan/procedures/report, bring-up guide, porting guide for MIPI pin-out/timing/ICD adaptation

- Formal design reviews (PDR, CDR, TRR) with AES/Sellmark; weekly status reporting; requirements clarification log

- Option A (if ordered): ONVIF stack — embedded Linux, RTSP/RTP server, ONVIF Device/Media/Imaging services, conformance testing, flash + source delivery

## 12.2 Out of Scope

- EMC/EMI certification (FCC/CE formal testing) — pre-compliance scan support quotable separately

- Environmental qualification: thermal cycling, vibration, shock, IP rating, HALT/HASS

- CoaXPress and USB3 Vision outputs — mentioned in the inquiry email but absent from the requirements document; quotable as future options

- Mechanical / enclosure design beyond compliance with the supplied O&M drawing

- Thermal camera core integration — any work involving the ITAR sensor, its drivers, or its ICD

- Host-side application software beyond standard GenTL consumers used for validation

- Production manufacturing beyond the prototype quantities (volume manufacturing quotable separately under Qmax Design-To-Manufacturing)

- Formal GigE Vision plugfest certification and associated travel

- Safety certifications (UL/IEC)

- Field support / warranty repairs beyond the warranty terms in Section 14

- Custom packaging, labeling or regulatory marking of prototypes

- Cybersecurity hardening / penetration testing (e.g., IEC 62443) — quotable separately

- Multi-language documentation — all deliverables in English

### Networking — Not Included

- VLAN support (802.1Q tagging)

- Time-Sensitive Networking (TSN)

- PTP / IEEE 1588 time synchronization — an optional feature in GigE Vision v2.x; image timestamps are derived from a free-running device clock, which is fully sufficient for single-camera operation. Network-synchronized timestamping (multi-camera rigs) is quotable as a change order.

- Jumbo frames beyond 9 KB MTU — note: jumbo frames up to 9 KB ARE included and are required for full-rate operation (Section 3.2); only MTU sizes beyond 9 KB are excluded.

- IPv6 — GigE Vision device discovery and streaming are IPv4-based; IPv4 (persistent / DHCP / LLA) is fully supported.

### Security — Not Included

- TLS / encrypted transport (not part of the GigE Vision protocol)

- Secure boot — excluded from scope; note the CertusPro-NX-50 silicon natively supports AES-256 bitstream encryption and ECDSA authentication, so secure boot can be enabled later as a change order without hardware changes.

- Payload or configuration encryption

- User authentication and role-based access control — GVCP/GigE Vision defines no authentication mechanism. Exception: the baseline HTTP-digest / WS-UsernameToken authentication mandated by ONVIF Profile S conformance IS included within Option A scope; anything beyond that baseline is excluded.

- FIPS 140 compliance or certification

### Camera / Image Processing Features — Not Included (Transparent-Bridge Principle)

The adapter board is a transparent transport bridge: pixels received on MIPI are delivered unmodified over Ethernet. All image-quality functions belong to the thermal camera core and are explicitly outside this scope:

- Auto exposure (AE)

- Automatic gain control (AGC / auto gain)

- Non-uniformity correction (NUC)

- Defective pixel detection / correction

- Image enhancement of any kind (sharpening, denoise, contrast/histogram, scaling, color processing)

- Any sensor-control loop — the design passes through pixel data and provides the GenICam register/feature plumbing; algorithm ownership remains with the camera core (consistent with the ITAR isolation in Assumption A-7)

# 13. Risk Register

Key program risks assessed likelihood (L) and impact (I) on a Low/Medium/High scale, with planned mitigations. The register is maintained live through the program and reviewed at every gate.

| ID | Risk | L | I | Mitigation / Contingency |
| --- | --- | --- | --- | --- |
| R-01 | From-scratch GigE Vision stack (Req. 7) fails conformance corner cases late in the program | M | H | Simulation-first protocol checkers from W1; incremental testing against AIA Validation Framework starting at first GVCP bring-up, not at the end; two independent host stacks (Aravis, eBUS) used throughout development |
| R-02 | 2.5 G SerDes ↔ PHY interoperability issues (autoneg, signal margin) | M | M | PHY candidate eval board tested against FPGA dev kit before CDR; SerDes eye-scan tuning in bring-up plan; alternate PHY footprint-compatible option identified at component selection |
| R-03 | Timing closure at 2.5 G line rate + 60 FPS pixel rate in selected FPGA | M | M | ≥25% utilization margin in device selection; early synthesis trial of MAC/GVSP datapath at PDR; speed-grade upgrade path retained |
| R-04 | Soft D-PHY RX implementation risk on CertusPro-NX HSIO (lane skew, HS/LP transitions) | M | M | Large margin: ~600 Mbps/lane required vs 1.5 Gbps HSIO capability; early hardware trial on CertusPro-NX eval board with reference camera before CDR; per-lane adjustable deskew in RTL |
| R-05 | FPGA / PHY component allocation or EOL during program | M | H | Lifecycle check at selection; long-lead parts for both spins ordered at schematic release; second-source options documented (Assumption A-15) |
| R-06 | 38 × 38 mm density: placement/routing infeasible with chosen FPGA package, or thermal limits exceeded | M | H | Placement feasibility study before PDR; HDI/via-in-pad stack-up options costed early; thermal estimate at architecture, measured at Spin 1; this is a prime driver for the included second spin |
| R-07 | PoE power budget exceeded (FPGA + PHY + 3.7 W sensor) | L | M | Power budget with 30% margin at architecture; 802.3at Class 4 (25.5 W) gives large headroom over ~8 W estimate (DRAM-less); measured at Spin 1 bring-up |
| R-08 | Requirement ambiguity (e.g., simultaneous RAW16+RGB888, ONVIF frame-rate expectation) discovered late | M | M | Assumptions A-4 / A-11 stated in proposal; clarification log baselined at kickoff; gate reviews include explicit requirement re-confirmation |
| R-09 | Reference OTS camera lacks RAW16 or full-rate 4-lane operation | M | L | Camera selection at PDR with datasheet-verified modes; internal pixel-exact test-pattern generator provides full-path coverage independent of camera (Assumption A-6) |
| R-10 | Sellmark-side porting to ITAR thermal core surfaces interface gaps after delivery | M | M | Parameterized CSI-2 RX (pin-out, lane mapping, timing); porting guide with worked example; optional remote consulting support quotable without ITAR data exchange |
| R-11 | Customer template/feedback delays (Req. 12/13, gate reviews) | M | M | Dependencies A-12–A-14 with day-for-day schedule relief; template-independent internal formats maintained so conversion is a final step |
| R-12 | Spin 1 findings exceed planned ECO effort (respin scope creep) | M | M | Two spins already budgeted (HW-13/HW-14); strict ECO scope control — only bring-up findings and DFM items enter Spin 2; new features deferred to change order |
| R-13 | Interpretation dispute over “no licensed IP” vs. FPGA hard primitives | L | H | Assumption A-3 submitted for written concurrence at kickoff, before architecture freeze |
| R-14 | Sustained 60 FPS soak failures (thermal, packet loss, buffer leaks) | M | M | 24-hour soak tests in Phase V4 on Spin 1 (early), repeated on Spin 2; instrumented frame counters and temperature logging built into the design for debug |
| R-15 | Limited on-chip resend window insufficient in customer’s deployed network topology (switched/congested) | L | M | Assumption A-17 submitted for Sellmark concurrence at kickoff; point-to-point deployment recommended in user documentation; fallback growth path documented (LFCPNX-100 with 7.3 Mb, or DRAM variant as change order) |

# 14. Terms & Conditions

## 14.1 Commercial

- Validity: this proposal is valid for 60 days from the date of issue.

- Pricing basis: engineering services at $ /hr (hardware) and $ hr (FPGA) against the effort estimates herein; estimates serve as not-to-exceed for the defined scope. Any scope change is executed only via written change order.

- Payment schedule (proposed): 25% advance with PO; 20% at PDR completion; 20% at CDR / Spin 1 release; 20% at first video over Ethernet; 15% at final delivery and acceptance.

- Payment terms: Net 30 days from invoice date. Late payments accrue interest at 1.5% per month.

- Material pass-through: prototype fabrication, assembly and components for both spins billed at cost with supporting documentation, plus applicable taxes, duties and freight.

- Taxes: prices exclude GST, sales tax, customs duties and withholding taxes, which are to the buyer’s account as applicable.

- Currency: all amounts in USD.

## 14.2 Scope & Change Management

- Requirements baseline: the customer requirements document, O&M drawing PT-DT21-0227 Rev 1, and the clarification log signed at kickoff constitute the baseline.

- Change orders: any deviation from the baseline (including derived clarifications) is handled via written change order with agreed effort and schedule impact before execution.

- Suspension / cancellation: upon cancellation, buyer pays for all work performed, non-cancellable material commitments, and an orderly wind-down of up to 80 hours.

## 14.3 Intellectual Property

- Deliverable IP: upon full payment, all project-specific deliverables — schematics, layout, RTL source, firmware source, testbenches and documentation — are assigned to the buyer with unrestricted rights, consistent with the intent of Requirement 7. Final wording per master agreement.

- Background IP: Qmax retains ownership of pre-existing tools, scripts and methodologies; any background IP embedded in deliverables is licensed royalty-free and perpetually for use within the deliverables.

- Third-party content: no third-party licensed HDL, IP cores or firmware will be incorporated (Req. 7). Any proposed open-source content (e.g., Linux components for Option A) is disclosed with license terms for buyer approval before use.

## 14.4 Confidentiality & Export Control

- Confidentiality: all exchanged information is governed by the NDA chain in effect (Sellmark–AES; AES–Qmax NDA to be executed if not already in place).

- ITAR / export compliance: Qmax will not receive, store or access ITAR-controlled technical data. Deliverables are developed exclusively against the commercial reference camera and the unclassified requirements provided. Each party is responsible for its own export-control compliance.

- Publicity: neither party references the other or the project publicly without prior written consent.

## 14.5 Warranty & Liability

- Workmanship warranty: prototypes are warranted against manufacturing workmanship defects for 90 days from delivery; remedy limited to repair or replacement. Prototypes are engineering samples, not production-qualified units.

- Design warranty: Qmax warrants that deliverables conform to the agreed requirements baseline at acceptance; non-conformances reported within 60 days of acceptance are corrected at no charge.

- Limitation of liability: total aggregate liability is capped at the fees paid under this engagement; neither party is liable for indirect, incidental or consequential damages, including loss of profit or data.

- End-application responsibility: buyer is responsible for qualification of the design within its end product, including regulatory compliance of the final product.

## 14.6 Delivery & Acceptance

- Delivery terms: prototype hardware shipped EXW Qmax facility or DAP buyer facility with freight at cost — Incoterms 2020, finalized at PO.

- Acceptance criteria: deliverables are accepted when the validation report demonstrates conformance to the requirements baseline and 20/20 Spin 2 units pass the functional screen. Acceptance is deemed granted if no written non-conformance is raised within 15 business days of delivery.

- Schedule: the ≈24-week schedule is indicative and assumes timely customer inputs (A-12 to A-14) and component availability (A-15).

## 14.7 General

- Force majeure: neither party is liable for delays from causes beyond reasonable control, including component allocation events, acts of government and natural disasters.

- Independent contractor: Qmax acts as an independent contractor; nothing herein creates a partnership, agency or employment relationship.

- Governing law / disputes: to be finalized at PO (e.g., State of California / Santa Clara County venue when contracting with Qmax Systems LLC, or laws of India / Chennai jurisdiction when contracting with Qmax Systems India Pvt. Ltd.; neutral arbitration such as SIAC available for India–US engagements).

- Order of precedence: master agreement (if any) → this proposal → purchase order. Pre-printed PO terms conflicting with this proposal do not apply unless expressly accepted in writing.